## Team Member 1 (Aldo)
Remaining Hours on Backlog Item
Log Date | Client Function of Networking | Server Function | Total Hours Remaining
2017-10-24 | 60 | 35 | 95
2017-10-25
2017-10-26
2017-10-27
2017-10-28
2017-10-29
2017-10-30
2017-10-31
2017-11-01
2017-11-02
2017-11-03
2017-11-04
2017-11-05
2017-11-06
2017-11-07
2017-11-08
2017-11-09
2017-11-10
2017-11-11
2017-11-12
2017-11-13
2017-11-14
2017-11-15
2017-11-16
2017-11-17
2017-11-18
2017-11-19
2017-11-20

## Team Member 2 (Ruben)
Remaining Hours on Backlog Item
Log Date | Min/Max Tree of AI | Alpha-Beta pruning | Iterative Deepening | Total Hours Remaining
2017-10-24 | 60 | 35 | 15 | 110
2017-10-25
2017-10-26
2017-10-27
2017-10-28
2017-10-29
2017-10-30
2017-10-31
2017-11-01
2017-11-02
2017-11-03
2017-11-04
2017-11-05
2017-11-06
2017-11-07
2017-11-08
2017-11-09
2017-11-10
2017-11-11
2017-11-12
2017-11-13
2017-11-14
2017-11-15
2017-11-16
2017-11-17
2017-11-18
2017-11-19
2017-11-20

## Team Member 3 (Alyssa)
Remaining Hours on Backlog Item
Log Date | Send Function in Game Manager | Receive in Game Manager | Update Game State | Total Hours Remaining
2017-10-24 | 60 | 35 | 15 | 110
2017-10-25 | 60 | 35 | 15 | 110
2017-10-26 | 60 | 35 | 15 | 110
2017-10-27 | 60 | 35 | 9 | 104
2017-10-28 | 60 | 35 | 9 | 104
2017-10-29 | 60 | 35 | 9 | 104
2017-10-30 | 52 | 34 | 7 | 93
2017-10-31 | 52 | 34 | 7 | 93
2017-11-01 | 52 | 34 | 7 | 93
2017-11-02 | 52 | 34 | 7 | 93
2017-11-03 | 52 | 34 | 2 | 88
2017-11-04
2017-11-05
2017-11-06
2017-11-07
2017-11-08
2017-11-09
2017-11-10
2017-11-11
2017-11-12
2017-11-13
2017-11-14
2017-11-15
2017-11-16
2017-11-17
2017-11-18
2017-11-19
2017-11-20

## Burndown Chart
Log Date | Reminaing Hours | Ideal Remaining
2017-10-24 |  | 315
2017-10-25 |  | 303.33
2017-10-26 |  | 291.66
2017-10-27 |  | 279.99
2017-10-28 |  | 268.32
2017-10-29 |  | 256.65
2017-10-30 |  | 244.98
2017-10-31 |  | 233.31
2017-11-01 |  | 221.64
2017-11-02 |  | 209.97
2017-11-03 |  | 198.3
2017-11-04 |  | 186.63
2017-11-05 |  | 174.96
2017-11-06 |  | 163.29
2017-11-07 |  | 151.62
2017-11-08 |  | 139.95
2017-11-09 |  | 128.28
2017-11-10 |  | 116.61
2017-11-11 |  | 104.94
2017-11-12 |  | 93.27
2017-11-13 |  | 81.6
2017-11-14 |  | 69.93
2017-11-15 |  | 58.26
2017-11-16 |  | 46.59
2017-11-17 |  | 34.92
2017-11-18 |  | 23.25
2017-11-19 |  | 11.58
2017-11-20 |  | 0

## Product Backlog
Product Backlog
GUI:
Buttons for pits, labeled with number of seeds it has
Register and Update State
Update seed count when clicked
Add a pictural representation of seeds in the pits
AI:
Random Moves
Test which move would be best for the immediate bound
Look 3 moves ahead
Look 10 moves ahead
Always Win
Min/Max Tree AI
Project Manager
Hold board info (how many seeds are in what pit?)
Call on AI for input
Call on user for input
Check for valid moves
Determine Winner
Client-Server Model
Sprint 1:
1) Call User/AI for input
2) Hold board info
3)Update the Bound
4)Check for valid moves
5)Determine Winner
6) AI that does random moves