## Team Member 1 (Aldo)
Remaining Hours on Backlog Item
Log Date | Client Function of Networking | Server Function | Total Hours Remaining
2017-10-24 | 60 | 35 | 95
2017-10-25 | 60 | 35 | 95
2017-10-26 | 60 | 35 | 95
2017-10-27 | 60 | 35 | 95
2017-10-28 | 60 | 35 | 95
2017-10-29 | 60 | 35 | 95
2017-10-30 | 60 | 35 | 95
2017-10-31 | 60 | 35 | 95
2017-11-01 | 60 | 35 | 95
2017-11-02 | 60 | 35 | 95 |  | Move Client function and Server function column to Alyssa, do GUI for Aldo
2017-11-03 | 60 | 35 | 95
2017-11-04 | 57 | 32 | 89 | <------------------ | Alyssa Started working on it from this point
2017-11-05 | 54 | 30 | 84
2017-11-06 | 51 | 28 | 79
2017-11-07 | 49 | 28 | 77
2017-11-08 | 49 | 28 | 77
2017-11-09 | 49 | 27 | 76
2017-11-10 | 47 | 26 | 73
2017-11-11 | 42 | 20 | 62
2017-11-12 | 35 | 15 | 50
2017-11-13 | 25 | 12 | 37
2017-11-14 | 18 | 8 | 26
2017-11-15 | 13 | 5 | 18
2017-11-16 | 13 | 5 | 18
2017-11-17 | 13 | 5 | 18
2017-11-18 | 13 | 5 | 18
2017-11-19 | 8 | 3 | 10
2017-11-20 | 6 | 1 | 7
11/21 | 0 | 0 | 0

## Team Member 2 (Ruben)
Remaining Hours on Backlog Item
Log Date | Min/Max Tree of AI | Alpha-Beta pruning | Iterative Deepening | Total Hours Remaining
2017-10-24 | 60 | 35 | 15 | 110
2017-10-25 | 60 | 35 | 15 | 110
2017-10-26 | 60 | 35 | 15 | 110
2017-10-27 | 60 | 35 | 15 | 110
2017-10-28 | 60 | 35 | 15 | 110
2017-10-29 | 60 | 35 | 15 | 110
2017-10-30 | 60 | 35 | 15 | 110
2017-10-31 | 60 | 35 | 15 | 110
2017-11-01 | 60 | 35 | 15 | 110
2017-11-02 | 60 | 35 | 15 | 110
2017-11-03 | 60 | 35 | 15 | 110
2017-11-04 | 55 | 35 | 15 | 105
2017-11-05 | 52 | 35 | 15 | 102
2017-11-06 | 52 | 30 | 15 | 97
2017-11-07 | 52 | 25 | 15 | 92
2017-11-08 | 52 | 25 | 15 | 92
2017-11-09 | 52 | 23 | 15 | 90
2017-11-10 | 52 | 23 | 15 | 90
2017-11-11 | 41 | 18 | 10 | 69
2017-11-12 | 31 | 13 | 8 | 52
2017-11-13 | 21 | 10 | 5 | 36
2017-11-14 | 11 | 5 | 3 | 19
2017-11-15 | 5 | 0 | 0 | 5
2017-11-16 | 0 | 0 | 0 | 0
2017-11-17 | 0 | 0 | 0 | 0
2017-11-18 | 0 | 0 | 0 | 0
2017-11-19 | 0 | 0 | 0 | 0
2017-11-20 | 0 | 0 | 0 | 0

## Team Member 3 (Alyssa)
Remaining Hours on Backlog Item
Log Date | Send Function in Game Manager | Receive in Game Manager | Update Game State | Total Hours Remaining
2017-10-24 | 60 | 35 | 15 | 110
2017-10-25 | 60 | 35 | 15 | 110
2017-10-26 | 60 | 35 | 15 | 110
2017-10-27 | 60 | 35 | 9 | 104
2017-10-28 | 60 | 35 | 9 | 104
2017-10-29 | 60 | 35 | 9 | 104
2017-10-30 | 52 | 34 | 7 | 93
2017-10-31 | 52 | 34 | 7 | 93
2017-11-01 | 50 | 34 | 3 | 87
2017-11-02 | 50 | 34 | 3 | 87
2017-11-03 | 50 | 34 | 3 | 87
2017-11-04 | 50 | 33 | 3 | 86 | <------------------ | Aldo Started Working on it from this point
2017-11-05 | 50 | 33 | 3 | 86
2017-11-06 | 50 | 33 | 3 | 86
2017-11-07 | 50 | 33 | 3 | 86
2017-11-08 | 48 | 33 | 3 | 84
2017-11-09 | 46 | 32 | 3 | 81
2017-11-10 | 46 | 32 | 3 | 81
2017-11-11 | 41 | 27 | 3 | 71
2017-11-12 | 37 | 22 | 1 | 61
2017-11-13 | 33 | 18 | 0 | 52
2017-11-14 | 26 | 18 | 0 | 45
2017-11-15 | 22 | 14 | 0 | 37
2017-11-16 | 18 | 10 | 0 | 29
2017-11-17 | 13 | 5 | 0 | 19
2017-11-18 | 8 | 2 | 0 | 11
2017-11-19 | 4 | 2 | 0 | 7
2017-11-20 | 4 | 0 | 0 | 5
11/21 | 0 | 0 | 0 | 0

## Burndown Chart
Log Date | Reminaing Hours | Ideal Remaining
2017-10-24 | 315 | 315
2017-10-25 | 315 | 303.33
2017-10-26 | 315 | 291.66
2017-10-27 | 309 | 279.99
2017-10-28 | 309 | 268.32
2017-10-29 | 309 | 256.65
2017-10-30 | 298 | 244.98
2017-10-31 | 298 | 233.31
2017-11-01 | 292 | 221.64
2017-11-02 | 292 | 209.97
2017-11-03 | 292 | 198.3
2017-11-04 | 280 | 186.63
2017-11-05 | 272 | 174.96
2017-11-06 | 262 | 163.29
2017-11-07 | 255 | 151.62
2017-11-08 | 253 | 139.95
2017-11-09 | 247 | 128.28
2017-11-10 | 247 | 116.61
2017-11-11 | 202 | 104.94
2017-11-12 | 163 | 93.27
2017-11-13 | 125 | 81.6
2017-11-14 | 90 | 69.93
2017-11-15 | 60 | 58.26
2017-11-16 | 47 | 46.59
2017-11-17 | 37 | 34.92
2017-11-18 | 29 | 23.25
2017-11-19 | 17 | 11.58
2017-11-20 | 12 | 0
11/21 | 0 | 0

## Product Backlog
Product Backlog
GUI:
| Buttons for pits, labeled with number of seeds it has |  |  | done kind of
Register and Update State
Update seed count when clicked
Add a pictural representation of seeds in the pits
AI:
| Random Moves |  |  | done
Test which move would be best for the immediate bound
| Look 3 moves ahead |  |  | done
| Look 10 moves ahead |  |  | done
Always Win
| Min/Max Tree AI |  |  | done
Project Manager
| Hold board info (how many seeds are in what pit?) |  |  | done
| Call on AI for input |  |  | done
| Call on user for input |  |  | done
| Check for valid moves |  |  | done
Determine Winner
Client-Server Model
Sprint 1:
| 1) Call User/AI for input |  |  | done
| 2) Hold board info |  |  | done
| 3)Update the Bound |  |  | done
| 4)Check for valid moves |  |  | done
| 5)Determine Winner |  |  | done
| 6) AI that does random moves |  |  | done
Sprint 2:
1) Register and Update State
| 2)Update Seed count when Clicked |  | kinda
| 3)Look 3 moves ahead |  | done
| 4)Look 10 moves ahead |  | done
| 5)Min/Max Tree AI |  | done
| 6)Client Server Model |  | done
Sprint 3
1)GUI Bounds
2)Update seed count when clicked
3)Add a pictural representation of seeds in the pits
4)Test which move would be best for the immediate bound
5)Hold board info (how many seeds are in what pit?)
6)Iterative Deeping