## Team Member 1 (Aldo)
Remaining Hours on Backlog Item
Log Date | Client Function of Networking | Server Function | Total Hours Remaining
2017-10-24 | 60 | 35 | 95
2017-10-25 | 60 | 35 | 95
2017-10-26 | 60 | 35 | 95
2017-10-27 | 60 | 35 | 95
2017-10-28 | 60 | 35 | 95
2017-10-29 | 60 | 35 | 95
2017-10-30 | 60 | 35 | 95
2017-10-31 | 60 | 35 | 95
2017-11-01 | 60 | 35 | 95
2017-11-02 | 60 | 35 | 95
2017-11-03 | 60 | 35 | 95
2017-11-04
2017-11-05
2017-11-06
2017-11-07
2017-11-08
2017-11-09
2017-11-10
2017-11-11
2017-11-12
2017-11-13
2017-11-14
2017-11-15
2017-11-16
2017-11-17
2017-11-18
2017-11-19
2017-11-20

## Team Member 2 (Ruben)
Remaining Hours on Backlog Item
Log Date | Min/Max Tree of AI | Alpha-Beta pruning | Iterative Deepening | Total Hours Remaining
2017-10-24 | 60 | 35 | 15 | 110
2017-10-25 | 60 | 35 | 15 | 110
2017-10-26 | 60 | 35 | 15 | 110
2017-10-27 | 60 | 35 | 15 | 110
2017-10-28 | 60 | 35 | 15 | 110
2017-10-29 | 60 | 35 | 15 | 110
2017-10-30 | 60 | 35 | 15 | 110
2017-10-31 | 60 | 35 | 15 | 110
2017-11-01 | 60 | 35 | 15 | 110
2017-11-02 | 60 | 35 | 15 | 110
2017-11-03 | 60 | 35 | 15 | 110
2017-11-04
2017-11-05
2017-11-06
2017-11-07
2017-11-08
2017-11-09
2017-11-10
2017-11-11
2017-11-12
2017-11-13
2017-11-14
2017-11-15
2017-11-16
2017-11-17
2017-11-18
2017-11-19
2017-11-20

## Team Member 3 (Alyssa)
Remaining Hours on Backlog Item
Log Date | Send Function in Game Manager | Receive in Game Manager | Update Game State | Total Hours Remaining
2017-10-24 | 60 | 35 | 15 | 110
2017-10-25 | 60 | 35 | 15 | 110
2017-10-26 | 60 | 35 | 15 | 110
2017-10-27 | 60 | 35 | 9 | 104
2017-10-28 | 60 | 35 | 9 | 104
2017-10-29 | 60 | 35 | 9 | 104
2017-10-30 | 52 | 34 | 7 | 93
2017-10-31 | 52 | 34 | 7 | 93
2017-11-01 | 50 | 34 | 3 | 87
2017-11-02 | 50 | 34 | 3 | 87
2017-11-03 | 50 | 34 | 3 | 87
2017-11-04
2017-11-05
2017-11-06
2017-11-07
2017-11-08
2017-11-09
2017-11-10
2017-11-11
2017-11-12
2017-11-13
2017-11-14
2017-11-15
2017-11-16
2017-11-17
2017-11-18
2017-11-19
2017-11-20

## Burndown Chart
Log Date | Reminaing Hours | Ideal Remaining
2017-10-24 | 315 | 315
2017-10-25 | 315 | 303.33
2017-10-26 | 315 | 291.66
2017-10-27 | 309 | 279.99
2017-10-28 | 309 | 268.32
2017-10-29 | 309 | 256.65
2017-10-30 | 298 | 244.98
2017-10-31 | 298 | 233.31
2017-11-01 | 292 | 221.64
2017-11-02 | 292 | 209.97
2017-11-03 | 292 | 198.3
2017-11-04 |  | 186.63
2017-11-05 |  | 174.96
2017-11-06 |  | 163.29
2017-11-07 |  | 151.62
2017-11-08 |  | 139.95
2017-11-09 |  | 128.28
2017-11-10 |  | 116.61
2017-11-11 |  | 104.94
2017-11-12 |  | 93.27
2017-11-13 |  | 81.6
2017-11-14 |  | 69.93
2017-11-15 |  | 58.26
2017-11-16 |  | 46.59
2017-11-17 |  | 34.92
2017-11-18 |  | 23.25
2017-11-19 |  | 11.58
2017-11-20 |  | 0

## Product Backlog
Product Backlog
GUI:
| Buttons for pits, labeled with number of seeds it has |  | done kind of
Register and Update State
Update seed count when clicked
Add a pictural representation of seeds in the pits
AI:
| Random Moves |  | done
Test which move would be best for the immediate bound
Look 3 moves ahead
Look 10 moves ahead
Always Win
Min/Max Tree AI
Project Manager
| Hold board info (how many seeds are in what pit?) |  | done
| Call on AI for input |  | done
| Call on user for input |  | done
| Check for valid moves |  | done
| Determine Winner |  | done
Client-Server Model
Sprint 1:
| 1) Call User/AI for input |  | done
| 2) Hold board info |  | done
| 3)Update the Bound |  | done
4)Check for valid moves
| 5)Determine Winner |  | done
| 6) AI that does random moves |  | done